## Sheet1
Pogvue 23rd December 2008 | Category | Priority | Complexity | Time (hours) | Date/time started | Date/time finished | Was the prediction correct?
************** Fix the display bug!!!!!!! ************************** | basic function | 0 | 2 | 3 |  |  |  | 6
Fix yscroll | basic function | 0 | 2 | 3 |  |  |  | 6 | Questions to ask :
Feature height proportional to score | basic function | 1 | 1 | 1 |  |  |  | 2
Names of repeats | basic function | 1 | 1 | 1 |  |  |  | 2 | I have the name of a gene
Distinguish tracks | beauty | 1 | 1 | 1 |  |  |  | 2
Scale with commas | beauty | 1 | 1 | 1 |  |  |  | 2 | Find the gene
More single key zoom levels | ease of use | 1 | 1 | 1 |  |  |  | 2
Make arrow keys work | ease of use | 1 | 1 | 1 |  |  |  | 2 | Where is it
Goto middle,start,end | ease of use | 1 | 1 | 1 |  |  |  | 2
Logos for the alignment | basic function | 1 | 1 | 2 |  |  |  | 4 | What is its structure
Graph display | basic function | 1 | 1 | 2 |  |  |  | 4
Fetch graphs - only fetch on sequence fetch in bottom panel | basic function | 1 | 1 | 2 |  |  |  | 4 | What are the characteristics of the gene (constraint, no exons, domains, promoter architecture, UTR architecture, no transcripts, likely function, how many paralogs, how many orthologs?)
Move tracks | ease of use | 1 | 1 | 2 |  |  |  | 4
Delete tracks | ease of use | 1 | 1 | 2 |  |  |  | 4 | What are the likely regulatory motifs and where are they?
Gene info display - description, pid etc, publications, GO, expression, | basic function | 1 | 1 | 3 |  |  |  | 6
Indel density (basic - not tree based) | basic function | 1 | 1 | 3 |  |  |  | 6 | Are there any known mutations or associations with disease?
UTRs on genes | basic function | 1 | 1 | 3 |  |  |  | 6
Strand displayed better - arrows etc | basic function | 1 | 1 | 3 |  |  |  | 6 | What genes share these regulatory motifs?
Fix AlignmentPanel | basic function | 1 | 2 | 8 |  |  |  | 16
Printing postscript | basic function | 1 | 2 | 3 |  |  |  | 6 | Are there any common combinations of motifs?
Drag to select search region | basic function | 1 | 2 | 3 |  |  |  | 6
Show chromosome and coords and no. base pairs in view | beauty | 1 | 2 | 3 |  |  |  | 6 | Common promoter architecture
Better labels | beauty | 1 | 2 | 3 |  |  |  | 6
Chromoview - context | beauty | 1 | 3 | 3 |  |  |  | 6 | Common UTR architecture
Bumping of labels | beauty | 1 | 2 | 4 |  |  |  | 8
Read maf | basic function | 1 | 3 | 8 |  |  |  | 16 | Similarly expressed genes
Better gene display | beauty | 1 | 2 | 3 |  |  |  | 6
Transparent overlay for bottom panel | beauty | 1 | 3 | 4 |  |  |  | 8 | Comparison to paralog architecture
zoom to whole gene, | ease of use | 2 | 1 | 1 |  |  |  | 2
zoom to promoter, | ease of use | 2 | 1 | 1 |  |  |  | 2 | Comparison to common domain architecture
Tab to next feature | ease of use | 2 | 1 | 1 |  |  |  | 2
Search panel for motifs | basic function | 2 | 1 | 2 |  |  |  | 4 | Similarly for a region.
Clearer fonts | beauty | 2 | 1 | 2 |  |  |  | 4
Column demarcation? | beauty | 2 | 1 | 2 |  |  |  | 4 | Similarly for a collection of genes, similarly expressed genes.
Quality scores in alignments | basic function | 2 | 2 | 3 |  |  |  | 6
Gaps in alignments - real or otherwise | basic function | 2 | 3 | 8 |  |  |  | 16 | Similarly for a collection of regions - e.g. chip seq. common kmers.
Colours - more transparency - find good examples of displaying data. Guardian,TED Tufte | beauty | 2 | 3 | 8 |  |  |  | 16
Progress bars - on loading, sequence fetching, searching | ease of use | 2 | 3 | 8 |  |  |  | 16 | Search transfac table with sequence.
menus and palettes | ease of use | 2 | 3 | 8 |  |  |  | 16
Scale logos by score | beauty | 3 | 1 | 3 |  |  |  | 6
Feature search | basic function | 3 | 2 | 3 |  |  |  | 6
Quickview for sequence. | ease of use | 3 | 3 | 8 |  |  |  | 16
Logos by clade | improved display | 3 | 3 | 8 |  |  |  | 16
Drag select to zoom | ease of use | 3 | 3 | 8 |  |  |  | 16
Bookmarking | ease of use | 3 | 3 | 16 |  |  |  | 32
Translation of genes | improved display | 3 | 3 | 16 |  |  |  | 32
Sequence and tree display | improved display | 3 | 3 | 3 |  |  |  | 6
Tree display for features | Ease of use | 3 | 3 | 3 |  |  |  | 6
Make obvious the bottom panel is blow up of the top panel | beauty | 3 | 3 | 4 |  |  |  | 8
Add gff features | basic function | 4 | 1 | 2 |  |  |  | 4
Alignment statistics - percent identity, coverage, feature density etc. | basic function | 4 | 1 | 3 |  |  |  | 6
Pwm generation from features | basic function | 4 | 2 | 4 |  |  |  | 8
Alignment coverage shadow. | basic function | 4 | 3 | 8 |  |  |  | 16
Make more use of colour and size - size by score | beauty | 4 | 3 | 8 |  |  |  | 16
Diced data - with gffs. Can we do this on the fly? | basic function | 4 | 4 | 8 |  |  |  | 16
Gene squeeze. | improved display | 4 | 4 | 16 |  |  |  | 32
Position of mutations on tree | basic function | 4 | 4 | 16 |  |  |  | 32
Position of indels on tree | basic function | 4 | 4 | 16 |  |  |  | 32
Gene comparison - cartoon comparison | improved display | 4 | 4 | 16 |  |  |  | 32
animations????? Root to human motif changes? | beauty | 5 | 5 | 0 |  |  |  | 4
Human - Rodent - Hedgehog - Dolphin motif changes. | beauty | 5 | 5 | 0 |  |  |  | 6
Separators between tracks | beauty | 5 | 1 | 4 |  |  |  | 8
Linkouts | ease of use | 5 | 1 | 3 |  |  |  | 6
Save to file | basic function | 5 | 2 | 3 |  |  |  | 6
List tracks | ease of use | 5 | 2 | 3 |  |  |  | 6
Change track colours | ease of use | 5 | 2 | 3 |  |  |  | 6
Colour sequence by clade | improved display | 5 | 2 | 3 |  |  |  | 6
Kmer frequencies | basic function | 5 | 3 | 3 |  |  |  | 6
Fade to grey when waiting for new data? | ease of use | 5 | 3 | 8 |  |  |  | 16
Default analysis of genes - conserved splice sites, conserved start and stop, TATA box polyA site, indels | basic function | 5 | 1 | 8 |  |  |  | 16
Domain display | basic function | 5 | 4 | 16 |  |  |  | 32
Fade in and out - when changing regions? | beauty | 5 | 4 | #VALUE! |  |  |  | ?
Fancy damped scrolling | beauty | 5 | 4 | #VALUE! |  |  |  | ?
'Adenosine!', 'Cytosine!', 'Thymine!', 'Guanine' - bugger! | fun | 10 | 3 | 0 |  |  |  | 16
Structure display | basic function | 10 | 10 | 0 |  |  |  | ?
Auto-zoom - | ease of use | ? | ? | 0 |  |  |  | ?
Distribution plots | ?? |  |  | 0 |  |  |  | ?
Transfac summary | ???? |  |  | 0 |  |  |  | ?
Simplify and clarify - not quite sure how to do this | hmmm |  |  | 0 |  |  |  | ?
|  |  |  | #VALUE! |  |  |  | #VALUE!
Beautify the display
Beautification??
Beautification